## Sheet1
# | Project Targets | Milestones | Key Activities | PIC | Start Date | End Date | Key Dependencies
3 | Establishment of CDH | Appointment of CDH Director, Manager, 2 IT staff, 2 Academician & 2 Data Analyst& Researcher | Finalise CDH organisational structure and job roles.; Obtain approval for staffing and budget. Recruit and appoint the Director, Manager, IT staff, academicians, and data analysts/researchers.; Onboard and operationalise the CDH team. | Dr Syahid/Prof. Ir. Faizal/Dr. Devasuda/Dr. Mizarina Abu Bakar | Q2 '25 | Q1 '26 | Management approval and budget availability.; HR support and timely recruitment processes.; Availability of qualified candidates. Provision of basic infrastructure and systems.
3 | Establishment of CDH | Soft setup | Appoint key personnel.; Establish basic operations and governance.; Procurement of machines and establish temporary facility. | Dr Syahid/Prof. Ir. Faizal/Dr. Devasuda | Q1 '26 | Q3 '26 | Management approval and budget availability.; HR support and availability of suitable candidates.
3 | Establishment of CDH | Commence 10 CPD trainings under AI Academy | Develop and finalise CPD training content.; Appoint trainers and subject matter experts.; Obtain required approvals and accreditation.; Promote and deliver 10 CPD programmes under the AI Academy. | Dr Syahid/Prof. Ir. Faizal | Q1 '26 | Q4 '26 | Availability of qualified trainers and subject matter experts.; Approval of CPD programmes and accreditation (e.g. CME/HRDC, where applicable).; Marketing and participant recruitment support.
3 | Establishment of CDH | Initiate 3 Digital Health Projects | Identify and scope three Digital Health projects, with priority for KPJ COE collaborations.; Form project teams and appoint leads.; Secure approvals, grants and commence project implementation. | Dr Syahid/Prof. Ir. Faizal | Q1 '26 | Q4 '26 | Availability of funding and resources.; Approval from management and relevant stakeholders.; Access to data, technology, and project partners.
3 | Establishment of CDH | CDH NEXUS AI & Digital Health Summit | Plan and organise the CDH NEXUS AI & Digital Health Summit.; Confirm speakers, programme content, and partnerships.; Promote and deliver the summit. | Dr Syahid/Prof. Ir. Faizal | Q1 '26 | Q4 '26 | Budget approval and sponsorship support.; Availability of speakers and partners.; Marketing, logistics, and administrative support.
3 | Establishment of CDH | CDH Digital Healthkathon | Conceptualise and plan the CDH Digital Health Hackathon.; Secure partners, mentors, and judges.; Promote, organise, and deliver the event. | Dr Syahid/Prof. Ir. Faizal | Q1 '26 | Q4 '26 | Budget and sponsorship approval.; Availability of technical infrastructure and mentors.; Marketing, logistics, and administrative support.